## Instructions
We will use Excel
· First tab is your Project Plan Make sure you state the Project Name (name of the technology solution)
· Second tab is Resources which is list of your team members and what skills they bring to the project.
Project Plan
Tasks - can add new tasks to provide more detail (remember to use a verb for example: Create Dashboard Wireframe, Create virtual server in AWS)
% completed
Start Date - this is your planned date and eventually will change to your actual date.
Finish Date - this may change as you realize that some tasks take longer than others. You put in the comments that the date changed and why.
Resource Name is the person who responsible to get this done. It may be a team who is working on it, yet there is one person who is leading the effort.
Notes - comments which explain the updates to the plan (i.e.. problems, accomplishments)

## Capstone Project Plan
| Task Name | % Complete | Start | Finish | Resource Name | Notes
Phase | Project Name: StockSphere | ~70% | Sep 7th | Nov 17th | Galen Watts
1 | SYSTEMS DESIGN | 100% | Sep 9th | Sep 15th | Galen Watts
| Process Map | 100% | Sep 9th | Sep 15th | Galen Watts
| Create User Interface (mockup) | 100% | Sep 9th | Sep 15th | Galen Watts
| Create Infrastructure Architecture (Network Topology) | 100% | Sep 9th | Sep 15th | Cody Spiller
| Create Information Architecture (ERD) | 100% | Sep 9th | Sep 15th | Brandon Velasquez
2 | SYSTEMS DEVELOPMENT | ~81% | Sep 7th | Nov 10th | Galen Watts
| Establish Development Environment | 100% | Sep 7th | Sep 22nd | Brandon Velasquez
| Create File Repo (Github) | 100% | Sep 7th | Sep 10th | Brandon Velasquez
| Test Development Environment | 100% | Sep 10th | Sep 22nd | Galen Watts / Brandon Velasquez
| Create User interface (webpages) | 52.5% | Oct 7th | Nov 3rd | Galen Watts
| Create Website Frameworks | 100% | Oct 7th | Oct 13th | Galen Watts
| Connect to Applications and Database | 5% | Oct 14th | Nov 3rd | Galen Watts | Other courses tests and scouting affected my time for this project on the original period.
| Create Application | 100% | Sep 30th | Oct 28th | Brandon Velasquez
| Create function to obtain information from Database | 100% | Sep 30th | Oct 13th | Brandon Velasquez
| Program Admin + Customer Functions | 100% | Oct 13th | Oct 28th | Brandon Velasquez
| Create Database | 100% | Sep 23rd | Oct 20th | Brandon Velasquez
| Create Database Foundation (Couchbase) | 100% | Sep 23rd | Oct 6th | Brandon Velasquez
| Implement Data Storage | 100% | Oct 7th | Oct 20th | Brandon Velasquez
| Deploy on cloud provider (AWS) | 50% | Nov 4th | Nov 10th | Brandon Velasquez
| Documentation | 40% | Oct 7th | Nov 17th | Galen Watts
| Mid-Build Deck | 100% | Oct 7th | Oct 13th | Galen Watts
| Build 1 Video | 100% | Oct 7th | Oct 13th | Galen Watts / Brandon Velasquez
| Final Build Deck | 0% | Nov 10th | Nov 20th | Galen Watts | Adjusted to give extra room
| Final Build Video | 0% | Nov 10th | Nov 20th | Galen Watts / Brandon Velasquez | Adjusted to give extra room
| Create Showcase Presentation | 0% | Nov 10th | Nov 20th | Galen Watts | Adjusted to give extra room

## Resources
Project Name: | Resources which is list of your team members and what skills they bring to the project.
Team Member | Skills | Notes
Brandon Velasquez | Databases (Couchbase), Progamming Knowledge, Github Knowledge | MDT
Galen Watts | HTML, Web Design, Management, Minor Video Editing | CDT